P&A PREPULL

PERRO ROJO 44 2

31.762, -102.009

API No.  42-329-34838

| Rig Consultant | Jay Hadesty 432-413-9302 |  |
| --- | --- | --- |
| Rig Supervisor | Ronnie Burnett 432-425-6534 |  |
| Production Foreman | Chris Falcon (432) 557-6145 |  |
| Company Engineer | David Smith (303) 550-0442 |  |
| RRC Engineer | S. Sommermeyer | (432) 684-5581 |
| HSE Coordinator | Chris Vasquez | (432) 528-4181 |
| Workover Supervisor | Doug Beaty (254) 477-3421 |  |

ALPHA Project – Wellhead Cut 30’ below grade

WELL:			PERRO ROJO 44 2
API:			42-329-34838
WELL CONFIG:		VERTICAL
PRODUCING STATUS:	SHUT IN
PRODUCING METHOD:	PUMPING ROD
FIELD:			BRYANT RANCH
COUNTY: 		MIDLAND
JOB CATEGORY:		ABANDON
JOB TYPE:		PLUG AND ABANDON
TA DATE:		N/A

AFE:			PA-001872PA

W3A Exp date:		12/16/2026
BATTERY INFO:		PERRO ROJO 44 (31.765, -102.01)
DATE:			2/5/2026

Action Plan

POOH, LD rods and tubing. Set CIBP @ +/-8167’. CBL dated 7/25/2003 indicates a TOC @ 3,066’. Pull 4-1/2” casing at 2,950’ as per CBL.

| P&A PROCEDURE |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # |  | DEPTH | SACKS |  | DESCRIPTION. |  |  |  |
| 1 |  | 8167’ | 3 |  | Set 4-1/2” CIBP @ +/-8167’. Est TOC – 3066’. |  |  |  |
| 2 |  | 6769’ – 6400’ | 40 |  | Spot. Tag top of plug. (Lowered to cover SA bottom) |  |  |  |
| 3 |  | 5600’ – 5400’ | 25 |  | Spot. Tag top of plug. (200’) |  |  |  |
| 4 |  | 4100’ – 4000’ | 40 |  | Perforate w/ 3-1/8” guns & squeeze. WOC 4 hrs & tag plug. |  |  |  |
| 5 |  | 3900’ – 3800’ | 40 |  | Perforate w/ 3-1/8” gun & squeeze. Tag plug. (May try to consolidate with #4) |  |  |  |
| - Cut and Recover 4-1/2” casing at 2950’ as per CBL, send casing to Cottons to be inspected. Use casing jacks if needed. Evaluate BOP needs and wellhead type. Use appropriate equipment. |  |  |  |  |  |  |  |  |
| 6 |  | 2000’ – 1800’ | 75 |  | Perforate w/ 3-1/8” gun & squeeze. Tag plug. (200’ plug) |  |  |  |
| 7 |  | 1000’ – 800’ | 75 |  | Perforate w/ 3-1/8” gun & squeeze. Tag plug. (200’ plug) |  |  |  |
| 8 |  | 322’ – 50’ | 160+ |  | POOH with tubing and shoot with 3-1/8” perf guns. Circulate cement up annulus to surface. WOC 4 hrs & tag top of plug. |  |  |  |
| - MIRU FORO Energy, make full internal (12-3/4” & 8-5/8”) casing cut at 10’ below surface grade – Pull casing |  |  |  |  |  |  |  |  |
| - Cut off wellhead (W3A indicates hole size for drilling surface was 17-1/2”) |  |  |  |  |  |  |  |  |
| - If casing does not pull, RU to wash over the outside of the 12-3/4” casing with a Texas pattern shoe and washover pipe |  |  |  |  |  |  |  |  |
| - Wash over down to 32 feet or until casing is loose, latch on to casing and pull |  |  |  |  |  |  |  |  |
| 9 |  | Top off as needed | 10+ sacks |  | Tag TOC ~50’ and cement up to casing cut |  |  |  |
| P&A COMMENTS |  |  |  |  |  |  |  |  |
| 1 | Notify Production Foreman Prior to Rigging Up |  |  |  |  |  |  |  |
| 2 | P&A JOB/AFE has been added. Edit job by inputting START DATE/ SERVICE CONTRACTORS/ JOB CONTACTS/ RIGS/ DAILY OPERATIONS/ TIME LOG/ DAILY COSTS/ DAILY CONTACTS |  |  |  |  |  |  |  |
| 3 | Pull tubing and re-shoot with bigger guns if injection rate cannot be established after perforating thru tubing. |  |  |  |  |  |  |  |
| 4 | If circulation up the annulus is achieved on the plug at 322’, calculate a larger cement volume to ensure cement is circulated to surface. |  |  |  |  |  |  |  |
| 5 | Notify Terry Medlin (817) 559-5441 at J&W Services to discuss if wellhead and valves should be sent to J&W or hauled off as scrap. |  |  |  |  |  |  |  |
| 6 | San Andres Depths: |  |  | TOP |  | 4406’ | BASE | 6719’ |